## Sheet1
YDF - FINANCE-SYSTEM TIMELINE PLAN
Project Start Date:
[5 empty] | AUGUST |  |  |  |  | SEPTEMBER | [28 empty] | OCTOBER | [30 empty] | NOVEMBER
[6 empty] | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Milestone Description | Assigned To | Progress | Start | Days | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Ledger creation | Oshen |  | 2025-11-14 | 7 | bar: 30 to 6
create, edit, delete, Report
voucher creation |  |  | 2025-11-21 | 6 | bar: 7 to 13
create, edit, delete, Report
Trial balance |  |  | 2025-11-27 | 6 | bar: 14 to 20
create, edit, delete, Report
accounts view |  |  | 2025-12-03 | 6 | bar: 21 to 27
create, edit, delete, Report
bank recnciliation |  |  | 2025-12-09 | 6 | bar: 28 to 4
create, edit, delete, Report
Income statement |  |  | 2025-12-15 | 6 | bar: 6 to 13
create, edit, delete, Report
balance sheet |  |  | 2025-12-21 | 6 | bar: 14 to 20
create, edit, delete, Report